## Form Responses 1 (hidden)
Timestamp | Untitled Question

## Test plan
TEST PLAN FOR "CALIFORNIA MARKETING"
General information
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
TEST PLAN
1 | Introduction | This document describes the methods and procedures that will be used in the testing process of the website. The objective of the testing activities is to check functions and features of a software product.
2 | Scope of project | The document mainly targets the Manual positive and negative testing, Automation testing with Selenium IDE, API with Postman and Performance testing with Lighthouse, GTMetrix and SpeedLab tools. The following components and functions would be tested for already registered user.
3 | Ouality objectives | A primary objective of testing is to: assure that the system meets the full requirements, including quality requirements (functional and non-functional requirements) and fit metrics for each quality requirement and satisfies the use case scenarios and maintain the quality of the product. The secondary objectives of testing will be to identify and expose all issues and associated risks, communicate all known issues to the project team, and ensure that all issues are addressed in an appropriate matter before release.
4 | Test approach | Analytical test approach was used, in accordance to requirements-based strategy, where an analysis of the requirements’ specification form is the basis for planning,estimating and designing tests. Test cases will be created during exploratory testing.
5 | Work plan | The parties are agreed to follow the next work plan: 1. Test plan preparation 2. Test plan approval. 3. Testing and bugs reporting. 4. Daily reports preparation. 5. Final report preparation.
6 | Requirements | REQ 1 | Verify login with valid email and password.
|  | REQ 2 | Verify that invalid email and valid password is entered.
|  | REQ 3 | Verify that login with valid email and password with 3 characters.
|  | REQ 4 | Verify the phone number in the “My account" included 10 integers is invalid.
|  | REQ 5 | Verify that user can add one more address to an account.
|  | REQ 6 | Verify that link on the site works.
|  | REQ 7 | Verify that user can enter on the section "Shop".
|  | REQ 8 | Verify that social media button "LinkedIn" is functional.
|  | REQ 9 | Verify that social media button "YouTube" is functional.
|  | REQ 10 | Verify that user can enter on the section "Blog".
|  | REQ 11 | Verify SignUp with Google.
|  | REQ 12 | Verify that valid email and incorrect password is entered.
|  | REQ 13 | Verify that user can add one more address in an account.
|  | REQ 14 | Verify that user can update Address in already existing account.
|  | REQ 15 | Verify that user can delete Address in already existing account.
7 | Test Case Execution | TC | Manual | Automation with Selenium IDE | API with Postman
|  | REQ 1/TC001-01 | x
|  | REQ 2/TC002-01 | x
|  | REQ 3/TC003-01 | x
|  | REQ 4/TC004-01 | x
|  | REQ 5/TC005-01 | x
|  | REQ 6/TC006-01 |  | x
|  | REQ 7/TC007-01 |  | x
|  | REQ 8/TC008-01 |  | x
|  | REQ 9/TC009-01 |  | x
|  | REQ 10/TC0010-01 |  | x
|  | REQ 11/TC0011-01 |  |  | x
|  | REQ 12/TC0012-01 |  |  | x
|  | REQ 13/TC0013-01 |  |  | x
|  | REQ 14/TC0014-01 |  |  | x
|  | REQ 15/TC0015-01 |  |  | x
8 | Test strategy | The objective of that testing is to make sure that the software product works according to the requirements, and no significant errors appear in the application. Entry Criteria ● The application construction is completed. ● The test engineers are dedicated. ● Necessary devices, instruments, and other equipment are acquired. ● Test environment is prepared, and the application is released to the test environment. ● Test environment is prepared, and the application is released to the test environment. Completion Criteria: ● All the planned tests are performed. ● There are no show-stopping errors. ● All the errors of high priority and severity are fixed. ● The test results are evaluated, discussed and approved.
9 | Resources and enviroment | Google Chrome 90.0.4430.85./Firefox 86.0./Safari 14.0.3. Mac OS Version 11.2.3.
10 | Testing process risks | The next issues may influence testing works: ● changes and modifications of the software product that were not planned and discussed with the test team beforehand; ● changes in the software requirements that were not discussed with the test team beforehand; ● delays in correcting/fixing errors; ● delays in delivering new builds to the test team.
11 | Test team expectations | The test team must be provided with valid, updated documents during the whole testing process. All the required equipment, instruments, devices and software must be acquired and prepared before beginning of the testing process. All show-stopping errors must be corrected as soon as possible. Release note should be added to each software release to the test team. The note must explain which elements, functions and features were added to the program and how these additions affect the software. The developers should correct all the errors in the software modules before releasing a new version.
12 | Deliverables | Test Plan. Bug reports and reports regarding the testing progress.

## Test Scenario
TEST SCENARIO "CALIFORNIA MARKETING"
Website: | https://qasvus.wixsite.com/ca-marketing
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-10
Total number of test cases | 15
Browser | Type of testing | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08
Google Chrome | Manual | x
| Automation | x
| API |  | x
| Performance |  | x
Safari | Manual |  |  | x
| Automation |  |  | x
| API |  |  |  | x
| Performance |  |  |  | x
Firefox | Manual |  |  |  |  | x
| Automation |  |  |  |  | x
| API | [5 empty] | x
| Performance | [5 empty] | x

## Test Cases Manual
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Types of testing: | Positive, negative,boundary and equivalence partitioning.
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
Test case ID | Test title (REQ) | Step description | Expected result | Actual result | Status (Done/Fail)
REQ 1
TC001-01 | Verify login with valid email and password. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User got into account. | As expected. | Done
2. Click on the button "Log in".
3. Click on the button "Log in with email".
4. Enter valid email and password.
5. Click "Log in".
REQ 2
TC002-01 | Verify that valid email and incorrect password is entered. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User should see "Wrong email or password". | Wrong explanation for mistake "An account with this email already exists". | Fail
2. Click on the button "Log in".
3. Click on the button "Log in with email".
4. Enter valid email and incorrect password "qwqw".
5. Click "Log in".
REQ 3
TC003-01 | Verify that login with valid email and password with 3 characters. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User should see "Password length must be between 4 and 100 characters". | As expected | Done
2. Find button "Log in". Click on it.
3. Pick "Sigh up" with email.
4. Enter valid email.
5. Enter password with 3 characters "q12".
6. Click on "Sing up".
REQ 4
TC004-01 | Verify the phone number in the “My account" included 10 integers is invalid. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User should see "Please enter valid phone number". | Information updated. | Fail
2. Find button "Log in". Click on it.
3. Enter valid email and valid password.
4. Click "Log in".
5. Go to My Accou on the top page.
6. In field Phone enter invalid characters for phone numbers such as 10 letter from A-Z.
REQ 5
TC005-01 | Verify that user can add one more address to an account. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see the New Address in an account. | As expected. | Done
2. Find button "Log in". Click on it.
3. Enter valid email and valid password.
4. Click "Log in".
5. Go to My Account on the top page.
6. Find the button "Add New Address".
7. Fill in all required information.
8. Push the button "Add Address".

## Test Cases Automation
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Types of testing: | Automation with Selenium IDE
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
Test case ID | Test title (REQ) | Step description | Expected result | Actual result | Status (Done/Fail)
REQ 6
TC006-01 | Verify that link on the site works. | Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see main page about marketing services. | Page has opened. | Done
REQ 7
TC007-01 | Verify that user can enter on the section "Shop". | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see different sections of shop. | As expected. | Done
2. Click on the button "Shop".
REQ 8
TC008-01 | Verify that social media button "LinkedIn" is functional. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see page of "LinkedIn". | As expected | Done
2. Find on the footer button "LinkedIn".
3. Click on it.
REQ 9
TC009-01 | Verify that social media button "YouTube" is functional. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see page of "LinkedIn". | As expected | Done
2. Find on the footer button "YouTube".
3. Click on it.
REQ 10
TC0010-01 | Verify that user can enter on the section "Blog". | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see Blog. | As expected. | Done
2. Click on the button "Blog".

## Test Cases API
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Types of testing: | Postman API
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
Test case ID | Test title (REQ) | Step description | Expected result | Actual result | Status (Done/Fail)
REQ 11
TC011-01 | Verify SignUp with Google. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User got into account. | As expected. | Done
2. Click on the button "Log in".
3. Click on the button "SignUp with Google".
4. Choose Google account for SignUp.
REQ 12
TC012-01 | Verify that valid email and incorrect password is entered. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User should see "Wrong email or password". | Wrong explanation for mistake "An account with this email already exists". But User can’t enter into an account. | Done
2. Click on the button "Log in".
3. Click on the button "Log in with email".
4. Enter valid email and incorrect password "qweert".
5. Click "Log in".
REQ 13
TC013-01 | Verify that user can add one more address in an account. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can see the New Address in an account. | As expected | Done
2. Find button "Log in". Click on it.
3. Enter valid email and valid password.
4. Click "Log in".
5. Go to My Account on the top page.
6. Find the button "Add New Address".
7. Fill in all required information.
8. Push the button "Add Address".
REQ 14
TC014-01 | Verify that user can update Address in already existing account. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can update Address in already existing account. | Information updated. | Done
2. Find button "Log in". Click on it.
3. Enter valid email and valid password.
4. Click "Log in".
5. Go to My Account on the top page.
6. Find the button "My addresses".
7. Push the button "Edit" and change any information.
8. Push the button "Update".
REQ 15
TC015-01 | Verify that user can delete Address in already existing account. | 1. Enter the https://qasvus.wixsite.com/ca-marketing in the browser. | User can delete Address in already existing account. | As expected. | Done
2. Find button "Log in". Click on it.
3. Enter valid email and valid password.
4. Click "Log in".
5. Go to My Account on the top page.
6. Find the button "My addresses".
7. Push the button "Remove".

## Test Report
TEST REPORT "CALIFORNIA MARKETING"
Website: | https://qasvus.wixsite.com/ca-marketing
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-10
Total number of test cases | 15
Status for
Number of test cases planned | 15
Number of test cases executed | 15
Number of test cases executed overall | 15
Number of defects encountered today | 2
Number of defect encountered so far | 2
Number of critical defects- still open | 0
Overall status
Number of test cases planned | 15
Number of test cases executed | 15
Pass Percentage of the defects | 13.33%
Defects density
Critical defects percentage | 13.33%

## Browser Compatibility Matrix
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
Browser compatibility |  | Mac OS Version 11.2.3.
Google Chrome | 90.0.4430.85. | x
Safari | 14.0.3. | x
Firefax | 86 | x

## Requirement Traceability Matrix
Project Name: | California marketing
Website: | https://qasvus.wixsite.com/ca-marketing
Test prepared by: | Inna Kryvdiuk
Test prepared by date: | 2021-05-03
Test executed by: | Inna Kryvdiuk
Test executed date: | 2021-05-10
D-test done
F-test fail
Business Requirement ID
Test Cases | REQ 1 | REQ 2 | REQ 3 | REQ 4 | REQ 5 | REQ 6 | REQ 7 | REQ 8 | REQ 9 | REQ 10 | REQ 11 | REQ 12 | REQ 13 | REQ 14 | REQ 15
TC001-01 | bar: Business Requirement ID REQ 1
TC001-02 | bar: Business Requirement ID REQ 1
TC001-03 | bar: Business Requirement ID REQ 1
TC002-01 | bar: Business Requirement ID REQ 2
TC002-02 | bar: Business Requirement ID REQ 2
TC002-03 | bar: Business Requirement ID REQ 2
TC003-01 | bar: Business Requirement ID REQ 3
TC003-02 | bar: Business Requirement ID REQ 3
TC003-03 | bar: Business Requirement ID REQ 3
TC004-01 | bar: Business Requirement ID REQ 4
TC004-02 | bar: Business Requirement ID REQ 4
TC004-03 | bar: Business Requirement ID REQ 4
TC005-01 | bar: Business Requirement ID REQ 5
TC005-02 | bar: Business Requirement ID REQ 5
TC005-03 | bar: Business Requirement ID REQ 5
TC006-01 | bar: Business Requirement ID REQ 6
TC006-02 | bar: Business Requirement ID REQ 6
TC006-03 | bar: Business Requirement ID REQ 6
TC007-01 | bar: Business Requirement ID REQ 7
TC007-02 | bar: Business Requirement ID REQ 7
TC007-03 | bar: Business Requirement ID REQ 7
TC008-01 | bar: Business Requirement ID REQ 8
TC008-02 | bar: Business Requirement ID REQ 8
TC008-03 | bar: Business Requirement ID REQ 8
TC009-01 | bar: Business Requirement ID REQ 9
TC009-02 | bar: Business Requirement ID REQ 9
TC009-03 | bar: Business Requirement ID REQ 9
TC0010-01 | bar: Business Requirement ID REQ 10
TC0010-02 | bar: Business Requirement ID REQ 10
TC0010-03 | bar: Business Requirement ID REQ 10
TC0011-01 | bar: Business Requirement ID REQ 11
TC0011-02 | bar: Business Requirement ID REQ 11
TC0011-03 | bar: Business Requirement ID REQ 11
TC0012-01 | bar: Business Requirement ID REQ 12
TC0012-02 | bar: Business Requirement ID REQ 12
TC0012-03 | bar: Business Requirement ID REQ 12
TC0013-01 | bar: Business Requirement ID REQ 13
TC0013-02 | bar: Business Requirement ID REQ 13
TC0013-03 | bar: Business Requirement ID REQ 13
TC0014-01 | bar: Business Requirement ID REQ 14
TC0014-02 | bar: Business Requirement ID REQ 14
TC0014-03 | bar: Business Requirement ID REQ 14
TC0015-01 | bar: Business Requirement ID REQ 15
TC0015-02 | bar: Business Requirement ID REQ 15
TC0015-03 | bar: Business Requirement ID REQ 15